## Sheet
Task | Task Overview | Timeline | Notes
VR App Development for Apple Vision Pro | Develop the core VR app to play 180° and 360° videos (both local and streamed). Dynamic content management will update videos without frequent app updates. | 3-4 weeks | Reuse existing video playback modules and develop the administration panel from scratch.
Administration Panel (Custom Built) | Create a custom admin panel that will allow the app owner to add new videos, descriptions, and graphics about the videos. | 2-3 weeks | Develop an intuitive and scalable admin panel from scratch.
Premium and Free Content Management | Implement logic to distinguish between free and premium content (e.g., titling videos as '[FREE] Movie name'). | 1 week | Minimal backend setup required.
Local Playback and Streaming Capabilities | Enable both offline playback and streaming. | 2-3 weeks | Develop streaming and offline capabilities from scratch.
In-App Purchases for Premium Videos | Integrate Apple in-app purchase for unlocking premium content. | 1 week | Use Apple’s standard in-app purchase mechanisms.
App Store Submission | Support publishing the app in the Apple Store. | 1 week | Standard app submission process.
Integration with GitLab | Set up a GitLab repository for source code and CI/CD pipeline. | 1-2 days | Quick setup for continuous integration and monitoring.